## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design
Develop iOS Compatible Mobile App
Develop Android Compatible Mobile App
Develop Web Portal application | Initial Architecture/Database Setup & Design | Basic Dashboard with heatmap display | Develop iOS Compatible Mobile App | Security Update
Upgrade Database | Manual Importing | User Based Preferences- Save Search & Reports | Develop Android Compatible Mobile App | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
Security Update | Authentication- Login/Logout | Export CSV of Reported Data | Upgrade Database | Automated Amber Alerts
Manual Importing | Basic Data Searching Capability | Web Report of Data (View only no Export) | Mobile App User Interface Refinement | Automated Integration for Importing
Automated Integration for Importing | Send Manual Amber Alerts by Region | Develop Web Portal application | Web Portal Redesign | In-App messaging for Doctors and Patients
Mobile App User Interface Refinement
Authentication- Login/Logout
Basic Dashboard with heatmap display
Basic Data Searching Capability
Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports
Web Portal Redesign
Export CSV of Reported Data
Send Manual Amber Alerts by Region
Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
Doctor | add the name of patients I have treated | I can add treatments | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | I want to be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low
CDC Official | see where the disease is most prevalent | Separating infested areas | As a CDC Official I can see where the disease is most prevalent so that Separating infested areas. | 1- user can use search area,system will give a result on the /2- system gives full details(Coordinates)
CDC Official | send funding and test kits specific area | Help reduce the spread of the virus | As a CDC Official I can send funding and test kits specific area so that Help reduce the spread of the virus. | 1. Users can initiate the fund sending process directly from the heat maps report.2.Users have access to a dedicated report page displaying all previously sent funds.
System Administrator | full control over user roles and access permissions | govern the system effectively and troubleshoot any issues that arise with user roles or access levels. | As a System Administrator I can full control over user roles and access permissions so that govern the system effectively and troubleshoot any issues that arise with user roles or access levels.. | 1.When accessing the system, the System Administrator should be able to view and modify user roles and access permissions. 2. The System Administrator should have the ability to troubleshoot and resolve any issues related to user roles or access.
System Administrator | ensure that the product information is accurately published and that the system is performing as intended | maintain the integrity and functionality of the system for all users. | As a System Administrator I can ensure that the product information is accurately published and that the system is performing as intended so that maintain the integrity and functionality of the system for all users.. | 1.Enable publishing and management of product information within the system.2.Provide monitoring tools and dashboards for tracking key performance metrics, including uptime, response times, and system usage.
Healthcare Company | report our production of virus test kits | contribute valuable data to the tracking efforts and ensure that our manufacturing output aligns with the demand for testing resources | As a Healthcare Company I can report our production of virus test kits so that contribute valuable data to the tracking efforts and ensure that our manufacturing output aligns with the demand for testing resources. | 1.Verify entered production quantity within reasonable bounds and expected format.2.Display confirmation message with timestamp upon receipt of information.
Healthcare Company | utilize the product to track the delivery of virus test kits. | proactively manage supply levels and coordinate with suppliers to address any shortages or delays | As a Healthcare Company I can utilize the product to track the delivery of virus test kits. so that proactively manage supply levels and coordinate with suppliers to address any shortages or delays. | 1.Enable users to promptly view shipment status and estimated arrival time.2.Implement email or in-app alerts for timely updates on delivery status changes.
Doctor | share successful treatment remedies | other healthcare professionals can benefit from effective treatment strategies | As a Doctor I can share successful treatment remedies so that other healthcare professionals can benefit from effective treatment strategies. | 1.Ensure mandatory fields completion for treatment remedy submissions.2.Verify submitted remedies for accuracy before acceptance
Doctor | access and learn from successful treatment remedies | enhance my understanding of effective treatment approaches, | As a Doctor I can access and learn from successful treatment remedies so that enhance my understanding of effective treatment approaches,. | 1.Organize treatment remedies for user-friendly browsing.2.Allow user ratings and comments for feedback and engagement.
Patient | report cases of the outbreak | ealth authorities can track and monitor the spread of the virus more effectively | As a Patient I can report cases of the outbreak so that ealth authorities can track and monitor the spread of the virus more effectively. | 1.Validate the information provided by patients to ensure accuracy and relevance.2.Enable patients to submit outbreak cases in real-time without delays.
Patient | track and monitor cases of the outbreak | stay informed about the current situation | As a Patient I can track and monitor cases of the outbreak so that stay informed about the current situation. | 1.Provide a user-friendly interface for patients to track outbreak cases.2Ensure that the tracking feature is accessible from various devices and platforms.
Test Center | log and report the usage of test kits | accurate data on test kit utilization is maintained, | As a Test Center I can log and report the usage of test kits so that accurate data on test kit utilization is maintained,. | 1.system allows test centers to log test kit usage accurately and efficiently.2.Verify that reported test kit usage aligns with actual consumption to maintain data integrity and inform resource allocation decisions.
Test Center | track the availability and consumption of test kits | proactively manage inventory levels, anticipate supply needs | As a Test Center I can track the availability and consumption of test kits so that proactively manage inventory levels, anticipate supply needs. | 1.Implement real-time tracking of test kit inventory to provide up-to-date information on availability and consumption.2.Set up alerts within the system to notify test centers when test kit inventory falls below predefined thresholds, enabling proactive replenishment planning.
Medical Examiner | report deaths caused by the outbreak | accurate and timely data on fatalities is available for public health authorities | As a Medical Examiner I can report deaths caused by the outbreak so that accurate and timely data on fatalities is available for public health authorities. | 1.Ensure mandatory fields completion for death reports.2.Validate submitted data to match required format and avoid errors.
Medical Examiner | access reports of deaths caused by the outbreak | analyze mortality trends over time | As a Medical Examiner I can access reports of deaths caused by the outbreak so that analyze mortality trends over time. | 1.access reports of virus-related deaths .2.Provide tools and dashboards for analyzing mortality trends over time.
Pharmaceutical Company | report test kit production quantities and delivery schedules | accurate data on test kit availability is provided to healthcare providers and authorities | As a Pharmaceutical Company I can report test kit production quantities and delivery schedules so that accurate data on test kit availability is provided to healthcare providers and authorities. | 1.Validate input for production quantities and delivery schedules.2.Ensure accurate data on test kit availability for resource allocation.
Pharmaceutical Company | track the status and location of test kit deliveries | ensure timely and reliable delivery of test kits to healthcare facilities | As a Pharmaceutical Company I can track the status and location of test kit deliveries so that ensure timely and reliable delivery of test kits to healthcare facilities. | 1. Provide real-time updates on delivery status and location.2.Enable pharmaceutical companies to ensure timely delivery to healthcare facilities.
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 1 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 3 | 6 | 2 Total Stories = 4 | 4
Doctor | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 2 | 4 | 3 Total Stories = 3 | 3
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | Release 1 (MVP) | 1 | 4 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered | Release 1 (MVP) | 3 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password | Release 2 | 5 | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 3 | 7 | 7 Total Stories = 3 |  |  | 3
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | Release 1 (MVP) | 3 | Sum | 10 | 10 | 5
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 2 | 5 | Total | 10 | 10 | 5 | 5
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | Release 1 (MVP) | 2 | SUM = TOTAL | #NAME? | #NAME? | #NAME?
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 1 (MVP) | 2
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | Release 2 | 5
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 1 (MVP) | 2
Test Center | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low | Release 3 | 7
CDC Official | As a CDC Official I can see where the disease is most prevalent so that Separating infested areas. | 1- user can use search area,system will give a result on the /2- system gives full details(Coordinates) | Release 1 (MVP) | 1
CDC Official | As a CDC Official I can send funding and test kits specific area so that Help reduce the spread of the virus. | 1. Users can initiate the fund sending process directly from the heat maps report.2.Users have access to a dedicated report page displaying all previously sent funds. | Release 3 | 6
System Administrator | As a System Administrator I can full control over user roles and access permissions so that govern the system effectively and troubleshoot any issues that arise with user roles or access levels.. | 1.When accessing the system, the System Administrator should be able to view and modify user roles and access permissions. 2. The System Administrator should have the ability to troubleshoot and resolve any issues related to user roles or access. | Release 1 (MVP) | 3
System Administrator | As a System Administrator I can ensure that the product information is accurately published and that the system is performing as intended so that maintain the integrity and functionality of the system for all users.. | 1.Enable publishing and management of product information within the system.2.Provide monitoring tools and dashboards for tracking key performance metrics, including uptime, response times, and system usage. | Release 2 | 5
Healthcare Company | As a Healthcare Company I can report our production of virus test kits so that contribute valuable data to the tracking efforts and ensure that our manufacturing output aligns with the demand for testing resources. | 1.Verify entered production quantity within reasonable bounds and expected format.2.Display confirmation message with timestamp upon receipt of information. | Release 1 (MVP) | 2
Healthcare Company | As a Healthcare Company I can utilize the product to track the delivery of virus test kits. so that proactively manage supply levels and coordinate with suppliers to address any shortages or delays. | 1.Enable users to promptly view shipment status and estimated arrival time.2.Implement email or in-app alerts for timely updates on delivery status changes. | Release 2 | 5
Doctor | As a Doctor I can share successful treatment remedies so that other healthcare professionals can benefit from effective treatment strategies. | 1.Ensure mandatory fields completion for treatment remedy submissions.2.Verify submitted remedies for accuracy before acceptance | Backlog for Future Release
Doctor | As a Doctor I can access and learn from successful treatment remedies so that enhance my understanding of effective treatment approaches,. | 1.Organize treatment remedies for user-friendly browsing.2.Allow user ratings and comments for feedback and engagement. | Backlog for Future Release
Patient | As a Patient I can report cases of the outbreak so that ealth authorities can track and monitor the spread of the virus more effectively. | 1.Validate the information provided by patients to ensure accuracy and relevance.2.Enable patients to submit outbreak cases in real-time without delays. | Release 2 | 4
Patient | As a Patient I can track and monitor cases of the outbreak so that stay informed about the current situation. | 1.Provide a user-friendly interface for patients to track outbreak cases.2Ensure that the tracking feature is accessible from various devices and platforms. | Backlog for Future Release
Test Center | As a Test Center I can log and report the usage of test kits so that accurate data on test kit utilization is maintained,. | 1.system allows test centers to log test kit usage accurately and efficiently.2.Verify that reported test kit usage aligns with actual consumption to maintain data integrity and inform resource allocation decisions. | Release 2 | 4
Test Center | As a Test Center I can track the availability and consumption of test kits so that proactively manage inventory levels, anticipate supply needs. | 1.Implement real-time tracking of test kit inventory to provide up-to-date information on availability and consumption.2.Set up alerts within the system to notify test centers when test kit inventory falls below predefined thresholds, enabling proactive replenishment planning. | Release 3 | 7
Medical Examiner | As a Medical Examiner I can report deaths caused by the outbreak so that accurate and timely data on fatalities is available for public health authorities. | 1.Ensure mandatory fields completion for death reports.2.Validate submitted data to match required format and avoid errors. | Release 2 | 4
Medical Examiner | As a Medical Examiner I can access reports of deaths caused by the outbreak so that analyze mortality trends over time. | 1.access reports of virus-related deaths .2.Provide tools and dashboards for analyzing mortality trends over time. | Release 2 | 4
Pharmaceutical Company | As a Pharmaceutical Company I can report test kit production quantities and delivery schedules so that accurate data on test kit availability is provided to healthcare providers and authorities. | 1.Validate input for production quantities and delivery schedules.2.Ensure accurate data on test kit availability for resource allocation. | Backlog for Future Release
Pharmaceutical Company | As a Pharmaceutical Company I can track the status and location of test kit deliveries so that ensure timely and reliable delivery of test kits to healthcare facilities. | 1. Provide real-time updates on delivery status and location.2.Enable pharmaceutical companies to ensure timely delivery to healthcare facilities. | Backlog for Future Release
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | 2
|  | As a Doctor I can login to the system so that I can enter patient treatment information. | 3
|  | As a CDC Official I can see where the disease is most prevalent so that Separating infested areas. | 3
| Sprint 2 | As a System Administrator I can give access to the system so that users can access,import, share data.. | 5
|  | As a Healthcare Company I can report our production of virus test kits so that contribute valuable data to the tracking efforts and ensure that our manufacturing output aligns with the demand for testing resources. | 0.5
|  | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | 2
|  | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 0.5
| Sprint 3 | As a System Administrator I can full control over user roles and access permissions so that govern the system effectively and troubleshoot any issues that arise with user roles or access levels.. | 5
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 2
|  | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | 1
Release 2 | Sprint 4 | As a Medical Examiner I can access reports of deaths caused by the outbreak so that analyze mortality trends over time. | 5
|  | As a Doctor I can add the name of patients I have treated so that I can add treatments . | 0.5
|  | As a Patient I can report cases of the outbreak so that ealth authorities can track and monitor the spread of the virus more effectively. | 1
|  | As a Test Center I can log and report the usage of test kits so that accurate data on test kit utilization is maintained,. | 1
|  | As a Medical Examiner I can report deaths caused by the outbreak so that accurate and timely data on fatalities is available for public health authorities. | 0.5
| Sprint 5 | As a Healthcare Company I can utilize the product to track the delivery of virus test kits. so that proactively manage supply levels and coordinate with suppliers to address any shortages or delays. | 1
|  | As a Healthcare Company I can reset my password by myself so that that I can login again. . | 2
|  | As a Patient I can change my test results so that the system data is accurate. | 2
|  | As a Healthcare Company I can utilize the product to track the delivery of virus test kits. so that proactively manage supply levels and coordinate with suppliers to address any shortages or delays. | 1
|  | As a System Administrator I can remove access so that users are not able to access the system. | 3
Release 3 | Sprint 6 | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | 3
|  | As a CDC Official I can send funding and test kits specific area so that Help reduce the spread of the virus. | 5
| Sprint 7 | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 2
|  | As a Test Center I can track the availability and consumption of test kits so that proactively manage inventory levels, anticipate supply needs. | 0.5
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 5